## William
Project Team Member | Itteration | Date of Activity | Duration (Minutes) | Activity Type | Short Description | Activity | Total Time
William Hebblewhite | 1 | 2022-03-03 | 60 | Meeting | Meeting b/w Company Directors + Leadership | Lecture | 240
William Hebblewhite | 1 | 2022-03-04 | 60 | Meeting | Meeting with Emily Chin to discuss Company Plans | Meeting | 930
William Hebblewhite | 1 | 2022-03-07 | 120 | Lecture | Weekly SIT782 Lecture | Mentoring | 150
William Hebblewhite | 1 | 2022-03-08 | 120 | Other | Created and Distributed a Team recruitment form to formalise team selections. | On-Track Tasks | 480
William Hebblewhite | 1 | 2022-03-08 | 60 | Other | Set up an Excel spread-sheet with Team distributions | Research | 180
William Hebblewhite | 1 | 2022-03-10 | 60 | Meeting | Meeting between Emily Chin & Myself to finalise teams and team leaders, discuss projects and project structures | Technical Work | 120
William Hebblewhite | 1 | 2022-03-11 | 120 | Other | Administrative work - Answering student questions regarding worklog, hours to contribute for specific grades, team distributions. | Up-Skilling | 60
William Hebblewhite | 1 | 2022-03-14 | 60 | Meeting | Weekly Lecture - Agile, Waterfall, Scrum refresh. | Other | 855
William Hebblewhite | 1 | 2022-03-14 | 120 | Other | Administrative work - Answering student questions regarding worklog
William Hebblewhite | 1 | 2022-03-14 | 60 | Meeting | First Meeting for the Data Science and Analysis team | TOTAL (Hours) | 50.25
William Hebblewhite | 1 | 2022-03-17 | 60 | Other | Set up Data Science Wiki, Data Science Logbooks and Connected to Teams
William Hebblewhite | 1 | 2022-03-18 | 60 | Research | Database and Database storage research
William Hebblewhite | 1 | 2022-03-17 | 60 | Meeting | Cohort Leadership meeting
William Hebblewhite | 1 | 2022-03-18 | 60 | Research | Free courses for AI-DS Cohort students to allow them to upskill.
William Hebblewhite | 1 | 2022-03-18 | 30 | Other | Documenting free courses for AI-DS Cohort students
William Hebblewhite | 1 | 2022-03-18 | 45 | Other | Developing a preliminary schedule for Redback Operations (to be discussed with team leads/Directors)
William Hebblewhite | 1 | 2022-03-18 | 60 | Other | Meeting to discuss Research and Next projects
William Hebblewhite | 1 | 2022-03-21 | 60 | Lecture | SIT782 Lecture
William Hebblewhite | 1 | 2022-03-24 | 60 | Research | Time-series regression algorithm research
William Hebblewhite | 1 | 2022-03-25 | 60 | Technical Work | Time-series regression algorithm research/Web-scrapping build prototype
William Hebblewhite | 1 | 2022-03-25 | 60 | Meeting | Data Science & Analysis team meeting
William Hebblewhite | 1 | 2022-03-26 | 150 | On-Track Tasks | Task 2.1P Draft
William Hebblewhite | 1 | 2022-03-27 | 120 | Meeting | Meeting with Sharni Sujatha to discuss Task 2.1P
William Hebblewhite | 1 | 2022-03-27 | 150 | On-Track Tasks | Task 2.1P Draft
William Hebblewhite | 1 | 2022-03-28 | 60 | Lecture | Weekly SIT782 Lecture
William Hebblewhite | 1 | 2022-03-29 | 90 | Meeting | Redback Operations Leadership Meeting
William Hebblewhite | 1 | 2022-04-01 | 60 | Meeting | Data Science & Analysis team meeting
William Hebblewhite | 1 | 2022-04-01 | 30 | On-Track Tasks | Submission 2.1P
William Hebblewhite | 1 | 2022-04-05 | 120 | Meeting | Redback Operations Leadership Meeting
William Hebblewhite | 1 | 2022-04-07 | 120 | Other | Various discussions and updates with Data Science and Analytics Team members
William Hebblewhite | 1 | 2022-04-08 | 60 | Meeting | Meeting with Data Engineering subteam to discuss file conversion, data pre-processing pipelines.
William Hebblewhite | 1 | 2022-04-09 | 150 | On-Track Tasks | Task Submission for Task 5.1D
William Hebblewhite | 1 | 2022-04-11 | 90 | Other | Contacting sub-team leaders regarding student contributions; Contributions to re-structuring company.
William Hebblewhite | 1 | 2022-04-12 | 60 | Up-Skilling | Undertook a Free Github refresh course via Udemy.
William Hebblewhite | 1 | 2022-04-12 | 60 | Meeting | Meeting w/ Directors to discuss Teams progress
William Hebblewhite | 1 | 2022-04-12 | 60 | Technical Work | Writing up documents related to data governance and ethics.
William Hebblewhite | 1 | 2022-04-12 | 30 | Other | Setting up Data Registry AND setting up new channels of communication.
William Hebblewhite | 1 | 2022-04-12 | 150 | Mentoring | Various discussions over the course of the semester related to mentoring

## Bowen
Project Team Member | Itteration | Date of Activity | Duration (Minutes) | Activity Type | Short Description | Activity | Total Time
Bowen Li | 1 | 7/3/2022 | 120 | Lecture | Lecture for SIT782 | Lecture | 600
Bowen Li | 1 | 14/3/2022 | 120 | Lecture | Lecture for SIT782 | Meeting | 180
Bowen Li | 1 | 15/3/2022 | 60 | Meeting | Squad meeting for preliminary assignment of tasks | Mentoring | 0
Bowen Li | 1 | 15/3/2022 | 120 | Up-Skilling | Upskilling on benchmark | On-Track Tasks | 0
Bowen Li | 1 | 16/3/2022 | 120 | Up-Skilling | Upskilling on Zwiftalizer | Research | 0
Bowen Li | 1 | 17/3/2022 | 120 | Up-Skilling | Upskilling on Peloton | Technical Work | 240
Bowen Li | 1 | 21/3/2022 | 120 | Lecture | Lecture for SIT782 | Up-Skilling | 750
Bowen Li | 1 | 23/3/2022 | 120 | Technical Work | Finish the personal team task | Other | 0
Bowen Li | 1 | 24/3/2022 | 120 | Technical Work | Optimize the code
Bowen Li | 1 | 24/3/2022 | 90 | Up-Skilling | Upskilling on data cleaning | TOTAL (Hours) | 29.5
Bowen Li | 1 | 25/3/2022 | 60 | Meeting | Team Meeting - With Individual updates on tasks
Bowen Li | 1 | 25/3/2022 | 60 | Up-Skilling | Upskilling on meraging data sets
Bowen Li | 1 | 28/3/2022 | 120 | Lecture | Lecture for SIT782
Bowen Li | 1 | 29/3/2022 | 90 | Up-Skilling | Watch Youtube video upskilling on exploring data and how to train model 1
Bowen Li | 1 | 30/3/2022 | 60 | Up-Skilling | Watch Youtube video upskilling on exploring data and how to train model 2
Bowen Li | 1 | 31/3/2022 | 90 | Up-Skilling | Watch Youtube video upskilling on exploring data and how to train model 3
Bowen Li | 1 | 1/4/2022 | 60 | Meeting | Weekly Team Meeting - Next set of Analysis Tasks
Bowen Li | 1 | 4/4/2022 | 120 | Lecture | Lecture for SIT782

## Langning
Project Team Member | Itteration | Date of Activity | Duration (Minutes) | Activity Type | Short Description | Activity | Total Time
langning bao | 1 | 2022-03-16 | 60 | On-Track Tasks | Task 1.1p | OnTrack task | 60
langning bao | 1 | 2022-03-07 | 120 | Lecture | Week one lecture | attending lectures | 120
langning bao | 1 | 2022-03-14 | 120 | Lecture | Week two lecture | attending lectures | 120
langning bao | 1 | 2022-03-21 | 120 | Lecture | Week three lecture | attending lectures | 120
langning bao | 1 | 2022-03-28 | 120 | Lecture | Week 4 lecture | attending lectures | 120
langning bao | 1 | 2022-04-04 | 120 | Lecture | Week 5 lecture | attending lectures | 120
langning bao | 1 | 2022-04-11 | 120 | Lecture | Week 6 lecture | attending lectures | 120
langning bao | 1 | 2022-04-25 | 120 | Lecture | Week 7 lecture | attending lectures | 120
langning bao | 2 | 2022-04-18 | 120 | Lecture | watched previous lectures | rewatching lecutres | 240
langning bao | 2 | 2022-03-17 | 60 | On-Track Tasks | Task 1.1p | OnTrack task | 60
langning bao | 1 | 2022-03-24 | 60 | On-Track Tasks | Task 1.1p | OnTrack task -completion | 60
Langning Bao | 1 | 2022-03-18 | 60 | Meeting | First Company meeting | attended meeting | 60
Langning Bao | 1 | 2022-03-25 | 45 | Meeting | company meeting | watched meeting recordings | 45
Langning Bao | 1 | 2022-04-01 | 30 | Meeting | company meeting | watched meeting recordings | 30
Langning Bao | 1 | 2022-04-22 | 20 | Meeting | company meeting | watched meeting recordings | 20
Langning Bao | 3 | 2022-04-17 | 120 | Other | reviewing materials from members of Redback | Reviewing materials | 360
Langning Bao | 3 | 2022-03-09 | 120 | Up-Skilling | Learning from online resources | Self-teaching | 360
Langning Bao | 3 | 2022-03-16 | 120 | Up-Skilling | Learning from online resources | Self-teaching | 360
Langning Bao | 3 | 2022-04-23 | 120 | Up-Skilling | Learning from online resources | Self-teaching | 360
Langning Bao | 3 | 2022-04-29 | 120 | Up-Skilling | Learning from online resources | Self-teaching | 360
Langning Bao | 3 | 2022-04-07 | 120 | Up-Skilling | Learning from online resources | Self-teaching | 360
Langning Bao | 3 | 2022-04-13 | 120 | Up-Skilling | Learning from online resources | Self-teaching | 360
Langning Bao | 3 | 2022-04-19 | 120 | Up-Skilling | Learning from online resources | Self-teaching | 360
Langning Bao | 3 | 2022-04-26 | 120 | Up-Skilling | Learning from online resources | Self-teaching | 360
Langning Bao | 2 | 2022-04-18 | 120 | Technical Work | Python coding (data-clearning and analysis) | Direct Contribution | 240
Langning Bao | 1 | 2022-04-19 | 120 | Technical Work | Python coding (data-clearning and analysis)-completed | Direct Contribution | 120
Langning Bao | 2 | 2022-04-20 | 120 | Technical Work | Coding a trainable model (steps vs cal burned) | Direct Contribution | 240
Langning Bao | 2 | 2022-04-21 | 120 | Technical Work | Coding a trainable model (steps vs cal burned)-completed | Direct Contribution | 240
Langning Bao | 3 | 2022-04-28 | 120 | Technical Work | Putting together a report to explain what the model does | Direct Contribution | 360
Langning Bao | 2 | 2022-02-22 | 120 | Technical Work | Report writing | Direct Contribution | 240
Langning Bao | 1 | 2022-04-29 | 60 | Meeting | company meeting | attended meeting | 60
[6 empty] | TOTAL (Hours) | 102.5833

## Shashvat
Project Team Member | Itteration | Date of Activity | Duration (Minutes) | Activity Type | Short Description | Activity | Total Time
|  | E.g 01/01/2022 Be sure to include dates only between Week 0 - Week 13 | 60 | Lecture | Please fill out with succint detail | Lecture | 60
|  |  | 20 | Meeting |  | Meeting | 20
|  |  | 30 | Mentoring |  | Mentoring | 30
|  |  | 45 | On-Track Tasks |  | On-Track Tasks | 45
|  |  | 60 | Research |  | Research | 60
|  |  | 80 | Technical Work |  | Technical Work | 80
|  |  | 100 | Up-Skilling |  | Up-Skilling | 100
|  |  | 120 | Other |  | Other | 120
[6 empty] | TOTAL (Hours) | 8.5833

## Andrew
Project Team Member | Itteration | Date of Activity | Duration (Minutes) | Activity Type | Short Description | Activity | Total Time
Andrew Mayes | 1 | 2022-03-07 | 60 | Lecture | Weekly SIT782 Lecture | Lecture | 180
Andrew Mayes | 1 | 2022-03-12 | 120 | On-Track Tasks | On-Track Task 1.1 | Meeting | 140
Andrew Mayes | 1 | 2022-03-13 | 60 | Meeting | Data Science & Analysis team meeting (Recording)
Andrew Mayes | 1 | 2022-03-14 | 60 | Lecture | Weekly SIT782 Lecture | Mentoring | 0
Andrew Mayes | 1 | 2022-03-21 | 120 | Research | Time series algorithms for predicting oxygen consumption | On-Track Tasks | 360
Andrew Mayes | 1 | 2022-03-21 | 60 | Lecture | Weekly SIT782 Lecture | Research | 360
Andrew Mayes | 1 | 2022-03-22 | 120 | Other | Research Summary
Andrew Mayes | 1 | 2022-04-10 | 60 | Meeting | Data Science & Analysis team meeting (Recording) | Technical Work | 240
Andrew Mayes | 1 | 2022-04-10 | 120 | Research | Time series algorithms for predicting oxygen consumption | Up-Skilling | 240
Andrew Mayes | 1 | 2022-04-10 | 120 | Technical Work | Creating Algorithm | Other | 120
Andrew Mayes | 1 | 2022-04-10 | 120 | Up-Skilling | Python and Pytorch
Andrew Mayes | 1 | 2022-04-18 | 20 | Meeting | Data Science & Analysis team meeting (Recording) | TOTAL (Hours) | 27.3333
Andrew Mayes | 1 | 2022-04-18 | 120 | Research | Time series algorithms for predicting oxygen consumption
Andrew Mayes | 1 | 2022-04-18 | 120 | Technical Work | Creating Algorithm
Andrew Mayes | 1 | 2022-04-18 | 120 | Up-Skilling | Python and Pytorch
Andrew Mayes | 1 | 2022-02-19 | 120 | On-Track Tasks | On-Track Task 6.1
Andrew Mayes | 1 | 2022-02-23 | 120 | On-Track Tasks | On-Track Task 6.1

## Lucy
Project Team Member | Iteration | Date of Activity | Duration (Minutes) | Activity Type | Short Description | Activity | Total Time
Lucy Mann | 1 | 2022-03-07 | 120 | Lecture | SIT378 week 1 class | Lecture | 735
Lucy Mann | 1 | 2022-03-07 | 30 | Other | Registering interest for Redback Operations through filling out online forms | Meeting | 695
Lucy Mann | 1 | 2022-03-09 | 90 | Up-Skilling | Brief refresher on working with databases (e.g. creating databases and implementing features) | Mentoring | 20
Lucy Mann | 1 | 2022-03-11 | 90 | Up-Skilling | Introduction to data analysis and data science (e.g. watching informational videos and reading online articles) | On-Track Tasks | 870
Lucy Mann | 1 | 2022-03-14 | 120 | Lecture | SIT378 week 2 class | Research | 360
Lucy Mann | 1 | 2022-03-14 | 60 | Meeting | Data Science and Analysis weekly team meeting | Technical Work | 360
Lucy Mann | 1 | 2022-03-16 | 90 | On-Track Tasks | Task 1.1P completion | Up-Skilling | 735
Lucy Mann | 1 | 2022-03-17 | 90 | Research | Data storage options research and summarisation | Other | 375
Lucy Mann | 1 | 2022-03-18 | 60 | Meeting | Data Science and Analysis weekly team meeting
Lucy Mann | 1 | 2022-03-19 | 60 | On-Track Tasks | Task 1.1P completion and submission | TOTAL (Hours) | 69.1667
Lucy Mann | 1 | 2022-03-19 | 10 | Other | Data Storage Solutions project task allocation on Trello
Lucy Mann | 1 | 2022-03-21 | 60 | Lecture | SIT378 week 3 class
Lucy Mann | 1 | 2022-03-22 | 90 | Research | Data storage options research and summarisation
Lucy Mann | 1 | 2022-03-23 | 30 | Meeting | Data Storage Solutions project meeting with Muzammil and Muhammad
Lucy Mann | 1 | 2022-03-25 | 60 | Research | Data storage options research and summarisation
Lucy Mann | 1 | 2022-03-25 | 60 | Meeting | Data Science and Analysis weekly team meeting
Lucy Mann | 1 | 2022-03-28 | 60 | Lecture | SIT378 week 4 class
Lucy Mann | 1 | 2022-03-28 | 30 | Meeting | Data Storage Solutions, Data Science, DevOps, IoT and Cyber Security leaders meeting
Lucy Mann | 1 | 2022-03-29 | 60 | On-Track Tasks | Task 5.1D completion
Lucy Mann | 1 | 2022-03-31 | 120 | Research | MongoDB vs. Firebase comparison research
Lucy Mann | 1 | 2022-04-01 | 30 | Meeting | Data Science and Analysis weekly team meeting
Lucy Mann | 1 | 2022-04-03 | 120 | On-Track Tasks | Task 5.1D completion
Lucy Mann | 1 | 2022-04-04 | 45 | Lecture | SIT378 week 5 class
Lucy Mann | 1 | 2022-04-05 | 120 | Up-Skilling | Up-skilling on MongoDB through MongoDB University
Lucy Mann | 1 | 2022-04-06 | 120 | Technical Work | Setting up MongoDB database testing environment
Lucy Mann | 1 | 2022-04-06 | 60 | On-Track Tasks | Task 5.1D completion and submission
Lucy Mann | 1 | 2022-04-07 | 20 | Mentoring | Teaching Data Storage Solutions project members how MongoDB works
Lucy Mann | 1 | 2022-04-08 | 30 | Meeting | Data Science and Analysis weekly team meeting
Lucy Mann | 1 | 2022-04-09 | 60 | Up-Skilling | Up-skilling on MongoDB through MongoDB University
Lucy Mann | 1 | 2022-04-11 | 30 | Lecture | SIT378 week 6 class
Lucy Mann | 1 | 2022-04-12 | 60 | On-Track Tasks | Task 6.1P completion
Lucy Mann | 1 | 2022-04-12 | 90 | Other | Data Storage Solutions Project roadmap completion
Lucy Mann | 1 | 2022-04-13 | 30 | Meeting | Database Solutions Meeting with Akshat, Mason and Michael
Lucy Mann | 1 | 2022-04-15 | 90 | On-Track Tasks | Task 6.1P completion
Lucy Mann | 1 | 2022-04-15 | 90 | Technical Work | Testing MongoDB database with sample dataset
Lucy Mann | 1 | 2022-04-16 | 90 | Up-Skilling | Up-skilling on MongoDB through MongoDB University
Lucy Mann | 1 | 2022-04-17 | 30 | On-Track Tasks | Task 6.1P completion
Lucy Mann | 1 | 2022-04-18 | 60 | Technical Work | Testing MongoDB database with sample dataset
Lucy Mann | 1 | 2022-04-18 | 30 | On-Track Tasks | Task 6.1P completion
Lucy Mann | 1 | 2022-04-20 | 60 | On-Track Tasks | Task 6.3C completion
Lucy Mann | 1 | 2022-04-20 | 45 | Meeting | Data Storage Solutions project meeting with Muzammil and Muhammad
Lucy Mann | 1 | 2022-04-21 | 20 | Other | Sprint Plan write-up
Lucy Mann | 1 | 2022-04-21 | 60 | On-Track Tasks | Task 6.3C completion and submission
Lucy Mann | 1 | 2022-04-22 | 30 | On-Track Tasks | Task 6.1P completion and submission
Lucy Mann | 1 | 2022-04-25 | 30 | Meeting | Watched Data Science and Analytics weekly meeting recording
Lucy Mann | 1 | 2022-04-25 | 45 | Other | Aims, goals, and processes write-up
Lucy Mann | 1 | 2022-04-25 | 60 | Lecture | SIT378 week 7 class
Lucy Mann | 1 | 2022-04-27 | 120 | Up-Skilling | Up-skilling on RESTful API
Lucy Mann | 1 | 2022-04-29 | 30 | Meeting | Data Science and Analysis weekly team meeting
Lucy Mann | 1 | 2022-05-02 | 60 | Lecture | SIT378 week 8 class
Lucy Mann | 1 | 2022-05-03 | 120 | Up-Skilling | Up-skilling on RESTful API
Lucy Mann | 1 | 2022-05-05 | 30 | Meeting | Team leader meeting with Mason (Cyber Security), Michael (Cyber Security) and Akshat (DevOps)
Lucy Mann | 1 | 2022-05-06 | 30 | Meeting | Data Storage Solutions project meeting with Muzammil and Muhammad
Lucy Mann | 1 | 2022-05-06 | 30 | Meeting | Data Science and Analysis weekly team meeting
Lucy Mann | 1 | 2022-05-07 | 45 | Other | Planning for company workshop
Lucy Mann | 1 | 2022-05-09 | 60 | Lecture | SIT378 week 9 class
Lucy Mann | 1 | 2022-05-10 | 90 | Technical Work | Testing MongoDB database with sample dataset
Lucy Mann | 1 | 2022-05-11 | 45 | Up-Skilling | Up-skilling on RESTful API
Lucy Mann | 1 | 2022-05-11 | 45 | Other | Planning for company workshop
Lucy Mann | 1 | 2022-05-12 | 120 | Meeting | Company workshop with Cyber Security and DevOps
Lucy Mann | 1 | 2022-05-13 | 30 | Meeting | Data Science and Analysis weekly team meeting
Lucy Mann | 1 | 2022-05-14 | 120 | On-Track Tasks | Task 10.1D completion and submission
Lucy Mann | 1 | 2022-05-15 | 20 | Meeting | Data Storage Solutions project meeting with Muzammil and Muhammad
Lucy Mann | 1 | 2022-05-16 | 120 | Lecture | SIT378 week 10 class
Lucy Mann | 1 | 2022-05-16 | 90 | Other | Data Storage Solutions system guide write-up

## Jack
Jack | Itteration | Date of Activity | Duration (Minutes) | Activity Type | Short Description | Activity | Total Time
|  | E.g 01/01/2022 Be sure to include dates only between Week 0 - Week 13 | 60 | Lecture | Please fill out with succint detail | Lecture | 60
|  |  | 20 | Meeting |  | Meeting | 20
|  |  | 30 | Mentoring |  | Mentoring | 30
|  |  | 45 | On-Track Tasks |  | On-Track Tasks | 45
|  |  | 60 | Research |  | Research | 60
|  |  | 80 | Technical Work |  | Technical Work | 80
|  |  | 100 | Up-Skilling |  | Up-Skilling | 100
|  |  | 120 | Other |  | Other | 120
[6 empty] | TOTAL (Hours) | 8.5833

## Hyun
Project Team Member | Itteration | Date of Activity | Duration (Minutes) | Activity Type | Short Description | Activity | Total Time
Hyun Dong Kim | 1 | 2022-03-07 | 120 | Lecture | Week 1 lecture | Lecture | 240
Hyun Dong Kim | 1 | 2022-03-08 | 15 | Other | Joining the "Red Back Opeartions" team and filling out some forms | Meeting | 220
Hyun Dong Kim | 1 | 2022-03-10 | 30 | Research | Research on health-related articles to see what the project is about (project research) | Mentoring | 0
Hyun Dong Kim | 1 | 2022-03-12 | 60 | Up-Skilling | Revisiting past studies (R, SIT720 Python and many more) | On-Track Tasks | 90
Hyun Dong Kim | 1 | 2022-03-13 | 120 | Up-Skilling | Started on git learning from LinkedIn (Still in progress) | Research | 150
Hyun Dong Kim | 1 | 2022-03-14 | 120 | Lecture | Week 2 lecture | Technical Work | 90
Hyun Dong Kim | 1 | 2022-03-14 | 60 | Meeting | Week 1 meeting | Up-Skilling | 180
Hyun Dong Kim | 1 | 2022-03-14 | 10 | Meeting | After the initial meeting with the team, I have initiated the sub-research group to have the members on board | Other | 35
Hyun Dong Kim | 1 | 2022-03-16 | 120 | Research | Research on benchmar (Zwift) and noting down interesting points
Hyun Dong Kim | 1 | 2022-03-17 | 60 | Meeting | Dicussing with teammates to see what points we could present in the weekly meeting (Documented) | TOTAL (Hours) | 16.75
Hyun Dong Kim | 1 | 2022-03-18 | 60 | Meeting | Weekly meeting & taking miniutes (script)
Hyun Dong Kim | 1 | 2022-03-18 | 30 | Meeting | Discussing with Shashvat on Wiki Page and Week 2 Meeting attendance & minutes
Hyun Dong Kim | 1 | 2022-03-18 | 90 | Technical Work | Making agenda & minute template and submitting for Week 2
Hyun Dong Kim | 1 | 2022-03-20 | 90 | On-Track Tasks | Tasks P1.1 Submission
Hyun Dong Kim | 1 | 2022-03-20 | 20 | Other | Wiki - file upload

## Gouri
Project Team Member | Itteration | Date of Activity | Duration (Minutes) | Activity Type | Short Description | Activity | Total Time
Gouri Nandan Reddy Gangavaram |  | 2022-03-07 | 120 | Lecture | Weekly Lecture for SIT782 | Lecture | 720
Gouri Nandan Reddy Gangavaram |  | 2022-03-14 | 120 | Lecture | Weekly Lecture for SIT782 - Agile, Waterfall, Scrum refresh. | Meeting | 480
Gouri Nandan Reddy Gangavaram |  | 2022-03-14 | 60 | Meeting | Team Meeting - Discussion of roles and responsibilities along with division of tasks and groups with intial goals mapped out. | Mentoring | 0
Gouri Nandan Reddy Gangavaram |  | 2022-03-16 | 120 | Research | Research into open-source data for Data Analysis | On-Track Tasks | 330
Gouri Nandan Reddy Gangavaram |  | 2022-03-17 | 45 | Research | Documentation of results found from researching open-source data available. | Research | 285
Gouri Nandan Reddy Gangavaram |  | 2022-03-18 | 60 | Meeting | Team Meeting - Discussion of results achieved through research about the availability of data and brainstorming of new tasks and ideas. | Technical Work | 360
Gouri Nandan Reddy Gangavaram |  | 2022-03-21 | 120 | Lecture | Weekly Lecture for SIT782 | Up-Skilling | 360
Gouri Nandan Reddy Gangavaram |  | 2022-03-23 | 120 | Up-Skilling | Upskilling in Python by following tutorials | Other | 0
Gouri Nandan Reddy Gangavaram |  | 2022-03-24 | 120 | Up-Skilling | Upskilling in Python for data cleaning & visualization
Gouri Nandan Reddy Gangavaram |  | 2022-03-25 | 60 | Meeting | Team Meeting - With Individual updates on tasks covered both as an individual and team over the week. | TOTAL (Hours) | 42.25
Gouri Nandan Reddy Gangavaram |  | 2022-03-25 | 60 | Meeting | Meeting with 'Anh Ling Le' (Teammate) in which he upskilled me in using Tableau software and using different plots and clean dataset.
Gouri Nandan Reddy Gangavaram |  | 2022-03-28 | 120 | Lecture | Weekly Lecture for SIT782
Gouri Nandan Reddy Gangavaram |  | 2022-03-29 | 120 | Up-Skilling | Tableue tool for better interpretation of results using Dashboards
Gouri Nandan Reddy Gangavaram |  | 2022-03-30 | 60 | Technical Work | Game Sales Analysis & Documentation
Gouri Nandan Reddy Gangavaram |  | 2022-03-31 | 60 | Technical Work | Game Sales Analysis & Documentation
Gouri Nandan Reddy Gangavaram |  | 2022-04-01 | 60 | Meeting | Weekly Team Meeting - Next set of Analysis Tasks
Gouri Nandan Reddy Gangavaram |  | 2022-04-02 | 150 | On-Track Tasks | Task 2.1P - Company Structure & Objectives
Gouri Nandan Reddy Gangavaram |  | 2022-04-04 | 120 | Lecture | Weekly Lecture for SIT782
Gouri Nandan Reddy Gangavaram |  | 2022-04-06 | 120 | Research | Research into open-source fitbit tracker analysis to relate towards exercise fitness
Gouri Nandan Reddy Gangavaram |  | 2022-04-08 | 120 | On-Track Tasks | Task 5.1D - Exemplary work and Leadership - Initial
Gouri Nandan Reddy Gangavaram |  | 2022-04-09 | 60 | On-Track Tasks | Task 5.1D - Exemplary work and Leadership - Initial
Gouri Nandan Reddy Gangavaram |  | 2022-04-11 | 120 | Lecture | Weekly Lecture for SIT782
Gouri Nandan Reddy Gangavaram |  | 2022-04-13 | 120 | Technical Work | Fitness dataset Feature Extraction and Cleaning of Data
Gouri Nandan Reddy Gangavaram |  | 2022-04-14 | 120 | Technical Work | Fitness dataset Analysis & Documentation
Gouri Nandan Reddy Gangavaram |  | 2022-04-20 | 60 | Meeting | Meeting with 'Anh Quan' (Teammate) to get insights and help each other out for upcoming tasks.
Gouri Nandan Reddy Gangavaram |  | 2022-04-22 | 60 | Meeting | Weekly Team Meeting - Sprint discussion
Gouri Nandan Reddy Gangavaram |  | 2022-04-22 | 60 | Meeting | Internal Games Sales Analysis Team Meeting - Sprint Goals and Tasks

## Anh Quan
Project Team Member | Itteration | Date of Activity | Duration (Minutes) | Activity Type | Short Description | Activity | Total Time
|  | E.g 01/01/2022 Be sure to include dates only between Week 0 - Week 13 | 60 | Lecture | Please fill out with succint detail | Lecture | 60
|  |  | 20 | Meeting |  | Meeting | 20
|  |  | 30 | Mentoring |  | Mentoring | 30
|  |  | 45 | On-Track Tasks |  | On-Track Tasks | 45
|  |  | 60 | Research |  | Research | 60
|  |  | 80 | Technical Work |  | Technical Work | 80
|  |  | 100 | Up-Skilling |  | Up-Skilling | 100
|  |  | 120 | Other |  | Other | 120
[6 empty] | TOTAL (Hours) | 8.5833

## Anh Linh
Project Team Member | Itteration | Date of Activity | Duration (Minutes) | Activity Type | Short Description | Activity | Total Time
ANH LINH LE | 1 | 2022-03-07 | 120 | Lecture | Week 1 Lecture | Lecture | 555
ANH LINH LE | 1 | 2022-03-07 | 45 | Other | Filling interest online form of Redback Operation | Meeting | 490
ANH LINH LE | 1 | 2022-03-08 | 90 | Up-Skilling | Visualizing by Seaborn (Python) | Mentoring | 290
ANH LINH LE | 1 | 2022-03-10 | 90 | Research | Reading Articles related to fitness analysis | On-Track Tasks | 660
ANH LINH LE | 1 | 2022-03-11 | 90 | Research | Reading Articles related to fitness analysis | Research | 660
ANH LINH LE | 1 | 2022-03-14 | 120 | Lecture | Week 2 Lecture | Technical Work | 390
ANH LINH LE | 1 | 2022-03-14 | 60 | Meeting | Data Science and Analytics team weekly meeting | Up-Skilling | 480
ANH LINH LE | 1 | 2022-03-15 | 120 | Research | Reading Articles related to fitness analysis | Other | 175
ANH LINH LE | 1 | 2022-03-16 | 120 | On-Track Tasks | Completing Task 1.1
ANH LINH LE | 1 | 2022-03-17 | 120 | Research | Finding datasets related to fitness analysis | TOTAL (Hours) | 61.6667
ANH LINH LE | 1 | 2022-03-18 | 60 | Meeting | Data Science and Analytics team weekly meeting
ANH LINH LE | 1 | 2022-03-18 | 90 | On-Track Tasks | Completing Task 1.1
ANH LINH LE | 1 | 2022-03-19 | 10 | Other | Task Allocation on Trello
ANH LINH LE | 1 | 2022-03-19 | 10 | Meeting | Discussing with Anh Quan
ANH LINH LE | 1 | 2022-03-21 | 120 | Lecture | Week 3 Lecture
ANH LINH LE | 1 | 2022-03-22 | 120 | Research | Datasets option and summarization
ANH LINH LE | 1 | 2022-03-25 | 60 | Meeting | Data Science and Analytics team weekly meeting
ANH LINH LE | 1 | 2022-03-25 | 120 | Mentoring | Guiding how to set up Tableau as well as seaborn with Anh Quan
ANH LINH LE | 1 | 2022-03-25 | 20 | Mentoring | Guiding how to set up Tableau as well as seaborn with Gouri
ANH LINH LE | 1 | 2022-03-27 | 90 | Up-Skilling | Cleaning data by Python
ANH LINH LE | 1 | 2022-03-28 | 120 | Lecture | Week 4 Lecture
ANH LINH LE | 1 | 2022-03-29 | 90 | Up-Skilling | Fix bug Python
ANH LINH LE | 1 | 2022-04-01 | 30 | Meeting | Data Science and Analytics team weekly meeting
ANH LINH LE | 1 | 2022-04-02 | 120 | On-Track Tasks | Completing Task 6.1
ANH LINH LE | 1 | 2022-04-04 | 45 | Lecture | Week 5 Lecture
ANH LINH LE | 1 | 2022-04-05 | 120 | Technical Work | Visualizing by Python
ANH LINH LE | 1 | 2022-04-06 | 150 | Mentoring | Guiding how to find and analyse the fitbit fitness dataset with Anh Quan
ANH LINH LE | 1 | 2022-04-08 | 90 | Up-Skilling | Analyzing by Python and Tableau
ANH LINH LE | 1 | 2022-04-09 | 120 | Research | Finding direction of analysing the insight of fitbit dataset
ANH LINH LE | 1 | 2022-04-11 | 30 | Lecture | Weel 6 Lecture
ANH LINH LE | 1 | 2022-04-12 | 120 | Other | Roadmap of Data Analytics team
ANH LINH LE | 1 | 2022-04-13 | 120 | Up-Skilling | Analyzing by Python (Panda profiling report)
ANH LINH LE | 1 | 2022-04-14 | 150 | On-Track Tasks | Completing Task 6.1
ANH LINH LE | 1 | 2022-04-15 | 120 | Technical Work | Fix bug Python
ANH LINH LE | 1 | 2022-04-16 | 120 | Meeting | Discussing with Anh Quan
ANH LINH LE | 1 | 2022-04-18 | 150 | Technical Work | Making the report of fitbit analysis
ANH LINH LE | 1 | 2022-04-20 | 60 | On-Track Tasks | Completing Task 6.1
ANH LINH LE | 1 | 2022-04-22 | 30 | Meeting | Data Science and Analytics team weekly meeting
ANH LINH LE | 1 | 2022-04-22 | 120 | Meeting | Discussing with Anh Quan
ANH LINH LE | 1 | 2022-04-23 | 120 | On-Track Tasks | Completing Task 6.3
ANH LINH LE | 1
ANH LINH LE | 1
ANH LINH LE | 1
ANH LINH LE | 1
ANH LINH LE | 1
ANH LINH LE | 1

## Muzammil
Project Team Member | Itteration | Date of Activity | Duration (Minutes) | Activity Type | Short Description | Activity | Total Time
|  | 2022-03-10 | 120 | Lecture | SIT378 week 1 class | Lecture | 435
|  | 2022-03-12 | 30 | Other | Registering interest for Redback Operations through filling out online forms | Meeting | 255
|  | 2022-03-16 | 120 | Up-Skilling | Started Linkeidn Learning course in Data Analysis using SQL | Mentoring | 0
|  | 2022-03-16 | 120 | Lecture | SIT378 week 2 class | On-Track Tasks | 480
|  | 2022-03-18 | 60 | Meeting | Data Science and Analysis weekly team meeting | Research | 270
|  | 2022-03-21 | 120 | On-Track Tasks | Task 1.1P completion | Technical Work | 120
|  | 2022-03-21 | 60 | Lecture | SIT378 week 3 class | Up-Skilling | 300
|  | 2022-03-22 | 60 | On-Track Tasks | Task 1.1P completion and submission | Other | 30
|  | 2022-03-22 | 90 | Research | Data storage options research and summarisation
|  | 2022-03-23 | 30 | Meeting | Data Storage Solutions project meeting | TOTAL (Hours) | 31.5
|  | 2022-03-25 | 60 | Research | Data storage options research (Azure, Workflow86 and SQL)
|  | 2022-03-25 | 60 | Meeting | Data Science and Analysis weekly team meeting
|  | 2022-03-28 | 60 | Lecture | SIT378 week 4 class
|  | 2022-03-31 | 120 | Research | Research on MongoDB
|  | 2022-04-01 | 30 | Meeting | Data Science and Analysis weekly team meeting
|  | 2022-04-04 | 45 | Lecture | SIT378 week 5 class
|  | 2022-04-05 | 120 | Up-Skilling | Up-skilling on MongoDB through MongoDB University
|  | 2022-04-06 | 120 | Technical Work | Clearing roadblocks in the testing environment of MongoDB
|  | 2022-04-08 | 30 | Meeting | Data Science and Analysis weekly team meeting
|  | 2022-04-09 | 60 | Up-Skilling | Up-skilling on MongoDB through MongoDB University
|  | 2022-04-11 | 30 | Lecture | SIT378 week 6 class
|  | 2022-04-14 | 120 | On-Track Tasks | Working on On track task 6.1p
|  | 2022-04-19 | 60 | On-Track Tasks | Working on On track task 6.1p
|  | 2022-04-20 | 45 | Meeting | Data Storage Solutions project meeting
|  | 2022-04-21 | 120 | On-Track Tasks | Completion of 6.1p and submission

## Vinay Ratta
Date Of Activity | Duration(In minutes) | Acticity Type | Short Description
2022-03-07 | 120 | Lecture | Attended Weekly Lecture - Learnt about the Companies and how we gonna join them.
2022-03-08 | 120 | Deakin sync | Watched Important videos uploaded by Andrew on unit site to get more familiar with the changes introduced in Capstone
2022-03-09 | 120 | Company Selection | Walked through the advertisements of different Companies for selection criteria and learning their focuses.
2022-03-10 | 120 | On Track Task | Start Doing On - track Task 1.1
2022-03-11 | 90 | On Track Task | Submitting On track Task 1.1
2022-03-14 | 120 | Lecture | Attended Weekly Lecture - Learnt about Agile/Scrum.
2022-03-14 | 60 | Team Meeting | Attended First Company Meeting after joining Data Science and Analytics Team - Got to learn about members of Team.
2022-03-15 | 60 | other | Went through the files uploaded by Team Lead like wiki, Team Log book.
2022-03-16 | 50 | other | Had a meeting with Team Lead and other Team member to decide on Time for weekly meetings
2022-03-17 | 45 | other | After Having Disagreements on Times, suggested my Whole Time and Team Leader to use the software WhenIsGood to vote up.
2022-03-01 | 120 | Up Skilling | Up Skilling In Python.
2022-03-01 | 60 | Cohorts | Leant about differnt Cohorts available and how can I contribute in these Cohorts.
2022-03-21 | 120 | Weekly Lecture | Attended Weekly Lecture for Week 3
2022-03-22 | 60 | Trello Board | Setting up Trello Board
2022-03-24 | 120 | Up Skilling | Learnt some basics for Machine Learning.
2022-03-25 | 60 | Notes | Preparing Notes for the Sub-Team Meeting.
2022-03-25 | 90 | other | Had a Team Meeting with my sub Team members to discuss how can we generate data.
2022-03-25 | 60 | Team Meeting | Attended Weekly Team Meeting - Learnt about the Team and start exploring the options to decide on Sub Teams
2022-03-26 | 60 | Trello Board | Setting up Colour Code as per Ongoing, Done and Future Tasks
2022-03-26 | 45 | On Track Task | Did Modifications in the submission for the On track Task 1.1 - as per requirements.
2022-03-28 | 120 | Weekly Lecture | Attended Weekly Lecture for Week 4
2022-04-01 | 60 | Team Meeting | Attended the company Team meeting - Data Science and Analytics - Learnt different roles in the Team - and stepped up to Lead the sub Team - Data Engineering
2022-04-02 | 120 | Up Skilling | Watched diffrerent Tutorials on to generate random values in data
2022-04-03 | 120 | Documentation | Produced a very basic document to learn the aspects of our Team
2022-04-04 | 120 | other | Had a meeting with Shashwat to discuss the issues our team is facing
2022-04-05 | 120 | Weekly Lecture | Attended Weekly Lecture for Week 5
2022-04-05 | 90 | other | Had a meeting with other Team member Shasvat to discuss about Integrating Training Data
2022-04-06 | 40 | Trello Board | Updating Trello Board
2022-04-07 | 120 | Up Skilling | Learnt Tableau and experimented with some data.
2022-04-08 | 120 | Up Skilling | Tableau and the data analysis.
2022-04-08 | 90 | Documentation | Made the Sprrint Document For out Sub Team to present in the team Weekly meeting.
2022-04-09 | 120 | On Track Task | Start Doing On - track Task 5.1 D
2022-04-10 | 60 | On Track Task | Finalise and Submit the On Track Task 5.1
2022-04-13 | 120 | Up Skilling | attended Deakin HelHub Session for my Python Queries.
2022-04-14 | 120 | Documentation | Produced Document to contribite to the showcase video
2022-04-15 | 60 | Team Meeting | Attended team meeting to share the work we have done so far
2022-04-15 | 120 | Team Meeting | Had a meeting with Shashwat to finalise the showcase document
Week 1 - 11 | 55 | Log Book | Spent 5 minutes every week to fill up the Log Book.
57.9167

## Xiaolu
Project Team Member | Itteration | Date of Activity | Duration (Minutes) | Activity Type | Short Description | Activity | Total Time
Xiaolu Li |  | 2022-03-07 | 75 | Lecture |  | Lecture | 70
Xiaolu Li |  | 2022-03-14 | 120 | Lecture |  | Lecture | 120
Xiaolu Li |  | 2022-03-14 | 60 | Meeting |  | Meeting | 60
Xiaolu Li |  | 2022-03-16 | 90 | Research | Benchamark research - Zwift | Reserach | 90
Xiaolu Li |  | 2022-03-17 | 45 | Research | Benchamark research - Peloton | Research | 40
Xiaolu Li |  | 2022-03-17 | 30 | other | Group Discussion | Discussion | 30
Xiaolu Li |  | 2022-03-18 | 60 | On-Track Tasks | 1.1 P | Ontrack | 60
Xiaolu Li |  | 2022-03-18 |  | Meeting | 60 | Meeting | 60
[6 empty] | TOTAL (Hours) | 8.8333

## ListOpt
Activity Types | Project Team Member | Duration (minutes)
Lecture | William Hebblewhite | 5
Meeting | Vinay Ratta | 10
Mentoring | Xiaolu Li | 20
On-Track Tasks | Bowen Li | 30
Research | Langning Bao | 45
Technical Work | Anh Linh Le | 60
Up-Skilling | Shashvat Joshi | 75
Other | Andrew Mayes | 80
| Jack Fleming | 90
| Gouri Nandan Reddy Gangavaram | 120
| Lucy Mann | 150
| Hyun Dong Kim | 180
Anh Quan Hua
Muzammil Raza